## Sheet1
Shree Shambhubhai V. Patel College of
Computer Science & Business Management, Surat
Daily Project Work Report (TY BCA)
Group No :- |  | Project Title :- eAuto – Bike Spare Parts E-Commerce
Platform
Front-End :- HTML,CSS,JavaScript,Bootstrap 5,AOS
(Animate On Scroll),PHP (for rendering UI and
sessions)
Back-End :- PHP (Core PHP for logic and server-side
Seat No | Name |  | processing),MySQL(Database),phpMyAdmin
423 | Dhruv Dholiya |  | (Database Management),XAMPP(Local
424 | Dharmik Dobariya |  | Development Server)
458 | Vatsal Kapadia | Project Guide :- Prof. Bipin Jadhav

## Sheet2
Sr. | Date | Module Name | Code/Design | DB Table | Doc Work | Description | URL | Sign
1 | 2025-07-15 | RG |  |  | Requirement Gatherin | Started requirement gathering
2 | 2025-07-16 | RG |  |  | Requirement Gatherin | Continued requirement collection
3 | 2025-07-17 | RG |  |  | Requirement Gatherin | Finalized requirement points
4 | 2025-07-18 | Analysis |  |  | Website Features | Identified user/admin website features
5 | 2025-07-19 | Analysis |  |  | Website Features | Detailed system feature planning
6 | 2025-07-20 |  |  |  |  | Holiday (Sunday)
7 | 2025-07-21 | Analysis |  |  | Website Features | Finalized features for development
8 | 2025-07-22 | Analysis |  |  | Website Features | Prepared use case diagram
9 | 2025-07-23 | Template |  |  |  | Collected user interface templates
10 | 2025-07-24 | Template |  |  |  | Finalized user-side templates
11 | 2025-07-25 | Template |  |  |  | Admin-side template analysis
12 | 2025-07-26 | Template |  |  |  | Selected final templates
13 | 2025-07-27 |  |  |  |  | Holiday (Sunday)
14 | 2025-07-28 | Database Design | ✔ | users, products, orders | ER Diagram | Created E-R diagram & table structure
15 | 2025-07-29 | Database Design | ✔ | users, products | Table Structure | Implemented `users`, `products` tables
16 | 2025-07-30 | Database Design | ✔ | orders, order_items | Table Structure | Implemented `orders`, `order_items` tables

## Sheet3
Sr. | Date | Module Name | Code/Design | DB Table | Doc Work | Description | URL | Sign
1 | 2025-07-31 | Admin Login | ✔ | admin |  | Developed admin login with session
2 | 2025-08-01 | User Registration | ✔ | users | Requirement Gatherin | Signup with validation
3 | 2025-08-02 | User Login | ✔ | users | Website Features | Login + session management
4 | 2025-08-03 |  |  |  |  | Holiday (Sunday)
5 | 2025-08-04 | Admin Dashboard | ✔ | products | Website Features | Add/edit/delete product features
6 | 2025-08-05 | Product Module | ✔ | products | Website Features | User-side product listing
7 | 2025-08-06 | Cart Module | ✔ | cart |  | Cart operations (add/update/delete)
8 | 2025-08-07 | Checkout Module | ✔ | orders, order_items |  | Address & payment selection
9 | 2025-08-08 | Order Placement | ✔ | orders, order_items |  | Address & payment selection
10 | 2025-08-09 | User Panel | ✔ | users, orders |  | Profile view/edit, order tracking
11 | 2025-08-10 |  |  |  |  | Holiday (Sunday)
12 | 2025-08-11 | Order History | ✔ | orders, order_items |  | List of past orders
13 | 2025-08-12 | Testing | ✔ | User Side |  | System testing and bug fixing
14 | 2025-08-13 | Testing | ✔ | Admin Side |  | System testing and bug fixing
15 | 2025-08-14 | Testing | ✔ | All Tables |  | System testing and bug fixing
16 | 2025-08-15 | Documentation | ✔ |  | Final Report | Completed project report